## Test Plan
Test ID | Test type | Planned / executed date | Responsible members | Scope | Tools / method | Status | Evidence reference
TP01 | Static code/syntax | 18–19 Aug 2026 | Kagiso; Ipeleng | Canonical PHP source | PHP linter; VS Code task | Passed | services/web syntax check
TP02 | Android unit/lint/build | 14 Aug 2026; repeat per change | Blessing; Masase | Android business rules/build | Gradle testDebugUnitTest; lintDebug; assembleDebug | Passed / repeat | Android build output
TP03 | API/database integration | 13–19 Aug 2026 | Kagiso; Blessing | Auth, RSVP, admin CRUD | PHP scripts; MySQL; health/ready | Partial | Fresh database rehearsal pending
TP04 | Responsive system | 13–19 Aug 2026 | Full team | Website flows and mobile layout | Browser at 1440/390/320 | Passed / repeat | docs screenshots
TP05 | Accessibility | Before pilot release | Ipeleng; Masase | TalkBack/VoiceOver; 200% scale | Physical devices; contrast | Planned | Manual evidence needed
TP06 | Password-reset delivery | Before pilot release | Blessing; Kagiso | Real code arrival/expiry | Verified sender + inbox | Planned | Email evidence needed
TP07 | UAT | Before client sign-off | Full team | Six elderly participants | UAT worksheet | Planned | No results yet

## Functional Test Log
Test ID | Requirement / feature | Preconditions | Steps | Expected result | Actual result | Status | Tester | Date | Evidence / defect ID
FT01 | PHP syntax | PHP installed | Run BKK syntax task | All PHP parses | Passed: canonical source parsed | Pass | Team | 18 Aug 2026 | Terminal/task output
FT02 | Responsive navigation | Website available | Open Home/Events at desktop and mobile widths | No overflow; navigation usable | Passed in recorded browser checks | Pass | Team | 13–19 Aug 2026 | docs/assets captures
FT03 | Android build | Android Studio/JDK | Run unit, lint and assemble tasks | Tests/lint/build succeed | Recorded successful build | Pass | Team | 14 Aug 2026 | Gradle output
FT04 | Duplicate RSVP | Database/API available | Confirm same event twice | One attendance record | Constraint/integration check recorded | Pass | Team | 13 Aug 2026 | API integration evidence
FT05 | Reset email | Verified sender/inbox | Request code using registered address | Code arrives, usable once | Not yet evidenced | Pending | Assign |  | Add inbox screenshot/message ID
FT06 | TalkBack/VoiceOver | Physical device | Complete sign-in + event flow | All controls announced/operable | Not yet tested | Pending | Assign |  | Add test video/notes

## UAT Log
Participant ID | Age range (optional) | Device | Task | Independent? | Assistance needed | Time / observation | Rating /5 | Issue / feedback | Follow-up owner | Status
UAT-01 |  |  | Find an event and RSVP | [6 empty] | Planned
UAT-02 |  |  | Find a pharmacy/restaurant discount | [6 empty] | Planned
UAT-03 |  |  | Find a local clinic/service | [6 empty] | Planned
UAT-04 |  |  | Submit a contact request | [6 empty] | Planned
UAT-05 |  |  | Update notification preferences | [6 empty] | Planned
UAT-06 |  |  | Reset password with email code | [6 empty] | Planned

## Defect Tracker
Defect ID | Date raised | Found by | Area | Summary | Severity | Status | Owner | Reproduction steps | Expected | Actual | Resolution / evidence
DEF-001 | [5 empty] | Open

## Evidence Register
Evidence ID | Test ID | Date | Environment | What it proves | File/link location | Reviewer | Result
EV-001 | FT01 | 18 Aug 2026 | Local PHP | Canonical PHP syntax check | Attach terminal output or CI log |  | Pass
EV-002 | FT03 | 14 Aug 2026 | Android | Unit/lint/debug assembly | Attach Gradle output/APK checksum |  | Pass
EV-003 | FT02 | 13–19 Aug 2026 | Browser | Responsive web screens | docs/assets web captures |  | Pass