## Overview
BKK Community Platform — Test Suite
Prepared from the WDP371 Student Guide. Baseline evidence dated 14 August and deployment/remediation evidence dated 20 August 2026 remain separated from tests that still require execution.
Item | Value | Verified status | Evidence date | Owner | Evidence reference
Live website | https://www.bkkcommunity.online | PASS — reachable | 2026-08-20 | Kagiso Mmatloa | live-verification-2026-08-20.json
API health | /health and /ready | PASS — 200; database connected | 2026-08-20 | Kagiso Mmatloa | live-verification-2026-08-20.json
Android app | Kotlin/Compose; minimum API 26 | PASS — build and API 26 device tests | 2026-08-14 | Ipeleng Sithole | elderly-core-2026-08-14.json
iOS companion | SwiftUI; iOS 16+ | PARTIAL — build/safety passed; full UI journey interrupted | 2026-08-14 | Ipeleng Sithole | elderly-core-2026-08-14.json
Website login gate | Signed-out users must land on Login | FAIL — Home and Discounts return 200 signed out | 2026-08-20 | Kagiso Mmatloa | DEF-001
Password reset | Random six-digit code by email | PARTIAL — known-account request accepted and active hashed token created; inbox consumption not witnessed | 2026-08-20 | Kagiso Mmatloa | Live request + DB token state; DEF-002 remains open
Security headers | HSTS, CSP and X-Content-Type-Options | PASS — CSP, HSTS, nosniff, DENY framing and referrer policy verified | 2026-08-20 | Kagiso Mmatloa | Post-deployment live header verification; DEF-003 closed
Real UAT | Six BKK participants aged 60+ | NOT RUN | Not supplied | Blessing Rugoyi | UAT Task Sheet
Administrator security | Migration 007, protected role grant, revalidation, timeouts, lifecycle and audit | PASS — deployed; isolated integration and signed-out route matrix passed | 2026-08-20 | Kagiso Mmatloa | docs/ADMIN_AUDIT_2026-08-20.md
Production backup | Protected MySQL backup and isolated restore verification | PASS — 15 tables and migration 007 restored; temporary database removed | 2026-08-20 | Kagiso Mmatloa | Protected operational record; backup excluded from GitHub
Functional execution summary
Total cases
PASS
FAIL
BLOCKED
NOT RUN
Pass rate

## Functional Test Cases
Functional Test Cases
Baseline automated/live evidence is retained. Post-remediation results are dated separately; remaining manual cases must not be marked PASS without evidence.
Test ID | Requirement ref | Category | Test description | Preconditions | Test steps | Expected result | Actual result | Status | Defect ID | Tested by | Test date | Evidence
FT-001 | FR6/NFR2 | Website | Open live Home page | Internet access | 1. Browse to live URL. 2. Wait for response. | Page loads over HTTPS without server error. | HTTP 200. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-002 | Auth policy | Security | Signed-out Home redirects to Login | No session cookie | 1. Clear cookies. 2. Open /. | 302/303 redirect to login.php. | HTTP 200 Home content visible. | FAIL | DEF-001 | Codex verification | 2026-08-20 | live JSON
FT-003 | Auth policy | Security | Signed-out Discounts redirects to Login | No session cookie | 1. Clear cookies. 2. Open /discounts.php. | Redirect to Login. | HTTP 200 Discounts content visible. | FAIL | DEF-001 | Codex verification | 2026-08-20 | live JSON
FT-004 | API availability | API | Health endpoint | Live deployment | GET /health. | 200 and status=ok. | 200 and status=ok. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-005 | API availability | API | Readiness and database connection | Live deployment | GET /ready. | 200, ready, database connected. | 200, ready, database connected. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-006 | FR1 | API | List published events | Live database | GET /api/v1/events. | 200 and array of events. | 200; labelled demonstration event returned. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-007 | FR3 | API | List active discounts | Live database | GET /api/v1/discounts. | 200 and discount data. | 200; three discount records returned. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-008 | FR4 | API | List local services | Live database | GET /api/v1/local-services. | 200 and service data. | 200; three service records returned. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-009 | Authentication | API | Register a new member | Unused disposable email | POST valid name, email and password. | 201; member token issued. | 201 during live lifecycle; account later deleted. | PASS |  | Codex verification | 2026-08-20 | live run notes
FT-010 | Authentication | API | Reject duplicate email | Existing disposable account | POST same registration again. | 409 conflict; no duplicate row. | 409 returned. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-011 | Authentication | API | Reject wrong password | Existing account | POST login with wrong password. | 401 without token. | 401 returned. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-012 | Profile | API | Read authenticated profile | Valid bearer token | GET /api/v1/me. | 200 and current member data. | 200 returned correct disposable profile. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-013 | Account deletion | API | Delete member account | Valid disposable account | DELETE /api/v1/me. | 200 and account removed. | 200 deleted=true. | PASS |  | Codex verification | 2026-08-20 | live JSON
FT-014 | Authentication | Website | Member sign-in | Configured test account | Enter valid email/password and submit. | Profile/Home displayed. | Passed in core journey. | PASS |  | Team automated journey | 2026-08-14 | elderly-core JSON
FT-015 | FR12/NFR5 | Website | Navigation and scrolling at 200% browser zoom | Chrome | Set zoom 200%; visit primary pages; scroll. | Content remains reachable and primary links usable. | Passed in Chrome mobile viewport journey. | PASS |  | Team automated journey | 2026-08-14 | elderly-core JSON
FT-016 | NFR6 | Android | Build and unit tests | Android project/JDK | Run debug build and unit tests. | Build succeeds; zero unit failures. | Build passed; 6 unit tests passed. | PASS |  | Team automated journey | 2026-08-14 | elderly-core JSON
FT-017 | FR9/NFR6 | Android | API 26 connected UI journey | API 26 emulator | Run connected device tests. | Login gate, recovery, registration, home, scrolling, schedule and safety pass. | 6 device tests passed. | PASS |  | Team automated journey | 2026-08-14 | elderly-core JSON
FT-018 | NFR5 | Android | Trackpad/mouse scrolling on Login | API 26 emulator | Scroll from fields to buttons. | All controls reachable. | Passed. | PASS |  | Team automated journey | 2026-08-14 | elderly-core JSON
FT-019 | Auth policy | Android | Logout returns to Login | Signed-in account | Open Me; tap Sign out. | Login screen displayed and token cleared. | Login screen displayed in current live-connected build. | PASS |  | Codex emulator verification | 2026-08-20 | android-logout-result.png
FT-020 | Password reset | API | Unknown-email reset response does not enumerate account | Live service | POST request for unregistered email. | 200 with neutral public message. | 200 neutral response returned. | PASS |  | Codex verification | 2026-08-20 | live request notes
FT-021 | Password reset | Email | Known member receives random six-digit code | Real inbox, verified sender | Register test account; request reset; inspect inbox. | One six-digit code received; code differs on next request. | Known-account request accepted and active hashed reset token created; mailbox receipt and code consumption not yet witnessed. | BLOCKED | DEF-002 | Codex verification | 2026-08-20 | Live request + DB token state; attach redacted inbox/reset evidence
FT-022 | Password reset | Security | Expired or used reset code is rejected | Issued test code | Use code; retry same code; test after expiry. | Reuse and expiry rejected. | Not run against real inbox flow. | NOT RUN |  | Unassigned
FT-023 | FR2 | Attendance | Confirm attendance online | Signed in; real test event | Open event; tap Attend. | Server confirms; UI shows Attending only after success. | Not run on a non-demonstration live event. | BLOCKED | DEF-006 | Unassigned |  | Need safe published test event
FT-024 | FR2 | Attendance | Cancel attendance | Existing attendance | Tap Cancel attendance. | Server confirms cancellation; history retained. | Not run on live real test event. | BLOCKED | DEF-006 | Unassigned
FT-025 | FR2 | Attendance | Duplicate RSVP prevented | Existing attendance | Submit Attend twice. | One user/event row; stable attending state. | Database script covers unique key; live UI retest pending. | NOT RUN |  | Unassigned
FT-026 | Offline rule | Android | RSVP does not show false success offline | Signed in; airplane mode | Open cached event; tap Attend. | Clear failure/offline message; no success state. | Not run. | NOT RUN |  | Unassigned
FT-027 | FR14 | Events | Filter events by category/date | Multiple published events | Select filters; clear filters. | Only matching events; empty state if none. | Not run with representative live content. | BLOCKED | DEF-006 | Unassigned
FT-028 | FR3/FR14 | Discounts | Filter discounts by category | Multiple categories | Select Pharmacy, Grocery, Restaurant. | Only matching active records shown. | Not run manually. | NOT RUN |  | Unassigned
FT-029 | FR4/FR13 | Services | Call and directions actions | Device with phone/maps | Open service; tap Call and Directions. | Correct number/destination passed to device app. | Not run on physical device. | BLOCKED | DEF-007 | Unassigned
FT-030 | FR5 | Contact | Submit valid contact message | Live service | Fill required fields and submit. | Confirmation shown; database message stored. | Scripted database test exists; live browser evidence pending. | NOT RUN |  | Unassigned
FT-031 | FR15 | Contact | Reject invalid/short contact input | Contact form | Submit invalid email and <10-character message. | Accessible validation message; no row stored. | Not run manually. | NOT RUN |  | Unassigned
FT-032 | FR10 | Admin | Create, edit, archive and restore event | Admin account | Log in as admin; create labelled test event; edit it; archive with reason; restore; verify member view and audit. | Changes persist, stale versions are rejected and lifecycle actions appear in Audit History. | Migration/account deployed; isolated MySQL event lifecycle, audit and stale-write tests passed. Authenticated production screenshots not captured. | BLOCKED | DEF-004 | Codex isolated integration | 2026-08-20 | docs/ADMIN_AUDIT_2026-08-20.md; live screenshots still required
FT-033 | FR11 | Admin | Create, edit, archive and restore discount | Admin account | Log in as admin; create labelled test discount; edit; archive with reason; restore; verify public view and audit. | Changes persist, stale versions are rejected and lifecycle actions appear in Audit History. | Migration/account deployed; isolated MySQL discount lifecycle and audit tests passed. Authenticated production screenshots not captured. | BLOCKED | DEF-004 | Codex isolated integration | 2026-08-20 | docs/ADMIN_AUDIT_2026-08-20.md; live screenshots still required
FT-034 | Admin | Admin | Manage services, messages and audit history | Admin account | Create/edit/archive/restore a labelled service; search/filter messages; change message status; inspect Audit History. | Database/public view update, message tools paginate/filter correctly and privileged actions are auditable. | Source and isolated MySQL service/message/audit journeys passed. Authenticated production screenshots not captured. | BLOCKED | DEF-004 | Codex isolated integration | 2026-08-20 | docs/ADMIN_AUDIT_2026-08-20.md; live screenshots still required
FT-035 | FR7 | Notifications | 24-hour event reminder | FCM configured; attending event | Enable reminders; wait/simulate scheduled worker. | One notification; deep link opens event. | Real Firebase credentials/device evidence absent. | BLOCKED | DEF-005 | Unassigned
FT-036 | FR8 | Notifications | New discount notification | FCM configured | Publish discount from admin. | Eligible devices receive one alert. | Not run; Firebase configuration absent. | BLOCKED | DEF-005 | Unassigned
FT-037 | Profile | Android/iOS | Notification preference persists | Signed-in member | Toggle each preference; relaunch; inspect server. | Value persists locally and on server. | Not run end-to-end. | NOT RUN |  | Unassigned
FT-038 | NFR1 | Accessibility | TalkBack/VoiceOver core tasks | Physical devices | Complete login, event, discount, contact with screen reader. | Labels read logically; all actions possible. | Human evidence not supplied. | BLOCKED | DEF-007 | Unassigned
FT-039 | NFR1 | Accessibility | 200% system font scale | Physical devices | Set 200%; repeat core tasks. | No clipped/unreachable text or controls. | Human evidence not supplied. | BLOCKED | DEF-007 | Unassigned
FT-040 | Security | HTTP | Required security headers | Live HTTPS | Inspect representative responses. | HSTS, CSP and nosniff present. | Live login returned CSP, HSTS, X-Content-Type-Options nosniff, X-Frame-Options DENY and strict referrer policy. | PASS |  | Codex verification | 2026-08-20 | Post-deployment live header verification; DEF-003 closed
FT-041 | UAT | Acceptance | Six-person elderly-user UAT | Six independent BKK participants 60+ | Run ten tasks and accessibility repeats; collect sign-off. | >=80% independent; average >=4/5; no critical defects. | No real participant evidence supplied. | BLOCKED | DEF-008 | Unassigned |  | UAT Task Sheet

## Responsive & Browser
Responsive and Cross-Browser Tests
Required desktop/tablet/mobile widths and browser/device combinations. Only evidence actually captured is marked PASS.
ID | Platform/browser | Viewport/device | Pages/tasks | Expected | Actual | Status | Tester | Date | Evidence
RB-001 | Chrome | 390 × 844 mobile viewport | Primary pages + 200% zoom | No horizontal loss; navigation and scroll usable | Passed in core journey | PASS | Team journey | 2026-08-14 | elderly-core JSON
RB-002 | Website | 375 px mobile | Home, Login, Events, Discounts, Info, Contact | Readable layout and 48px controls | Current screenshots available for Home only | NOT RUN |  |  | Capture all pages
RB-003 | Website | 768 px tablet | All member pages | Grid adapts; no overlap | No current evidence | NOT RUN
RB-004 | Website | 1440 px desktop | Home and Events | Centered shell; readable line lengths | Existing coded screenshots in repository | PASS | Project team | 2026-08-13 | docs/assets
RB-005 | Safari | Current macOS/iOS | Register, Login, Reset, navigation | Same functional result as Chrome | Not executed | NOT RUN
RB-006 | Firefox | Current desktop | All primary pages | Same functional result as Chrome | Not executed | NOT RUN
RB-007 | Edge | Current desktop | All primary pages | Same functional result as Chrome | Not executed | NOT RUN
RB-008 | Android | API 26 emulator | Login, recovery, register, Home, schedule | Works on minimum supported OS | 6 connected device tests passed | PASS | Team journey | 2026-08-14 | elderly-core JSON
RB-009 | Android | Current physical device | Full member journey + notifications | All tasks pass | Physical-device evidence absent | BLOCKED |  |  | DEF-005/007
RB-010 | iOS | iPhone simulator / iOS 26.5 | Fresh launch | Login is first screen | Passed | PASS | Team journey | 2026-08-14 | elderly-core JSON
RB-011 | iOS | Physical iPhone iOS 16+ | Full member journey | All tasks pass | Not executed | BLOCKED |  |  | Need physical-device/UAT evidence

## Performance Results
Performance Results
NFR2 target: <=3 seconds on broadband and <=6 seconds on mobile. No Lighthouse score is invented; the current public PageSpeed attempt was rate-limited.
ID | Target/page | Network/device | Metric | Pass criterion | Observed | Status | Tool | Date | Evidence
PF-001 | GET /health | Live HTTPS | Availability | HTTP 200 | HTTP 200 | PASS | HTTP client | 2026-08-20 | live JSON
PF-002 | GET /ready | Live HTTPS | Database readiness | HTTP 200 + connected | HTTP 200 + connected | PASS | HTTP client | 2026-08-20 | live JSON
PF-003 | Home 1440 | Broadband desktop | LCP / load time | <=3s; Lighthouse >=80 | PageSpeed API returned 429; no score | BLOCKED | Lighthouse/PageSpeed | 2026-08-20 | Repeat locally or DevTools
PF-004 | Home 375 | Simulated mobile | LCP / load time | <=6s; Lighthouse >=80 | Not measured | NOT RUN | Lighthouse
PF-005 | Events API | 25 concurrent users | p95 latency/error rate | p95 <2s; <1% errors | Not load tested | NOT RUN | k6/JMeter
PF-006 | Android cold launch | API 26 + current phone | Time to interactive | <=5s on test device | Not timed | NOT RUN | Android Profiler
PF-007 | Android screen change | Current phone | UI responsiveness | No visible >100ms main-thread stall | User reported slowness; profiler evidence absent | BLOCKED | Android Profiler |  | DEF-009

## Security Checklist
Security Checklist
Security controls are assessed against implemented code, isolated integration and the deployed service. Baseline failures remain in the Defect Log; secrets must never be pasted into this workbook.
ID | Control/test | Threat | Method | Expected | Observed | Status | Severity | Date | Evidence/defect
SC-001 | Passwords hashed | Credential disclosure | Inspect auth/reset code | password_hash/password_verify; no plaintext | Implemented | PASS | Critical | 2026-08-20 | app/auth.php; password_reset.php
SC-002 | Reset code unpredictability | Code prediction | Inspect generator | CSPRNG-generated six digits | random_int(0,999999) | PASS | High | 2026-08-20 | password_reset.php
SC-003 | Reset token at rest | Database disclosure | Inspect schema/code | Only keyed hash stored | HMAC-SHA256 token_hash | PASS | High | 2026-08-20 | schema.sql; password_reset.php
SC-004 | Reset expiry/attempt limit | Brute force/replay | Inspect code/schema | 15-minute expiry; <=5 attempts; single use | Implemented in transaction | PASS | High | 2026-08-20 | password_reset.php
SC-005 | Account enumeration | Email discovery | Request reset for unknown email | Neutral status/message | 200 neutral response | PASS | Medium | 2026-08-20 | FT-020
SC-006 | Prepared SQL | SQL injection | Inspect repository/API | User input bound to prepared statements | Implemented in sampled modules | PASS | Critical | 2026-08-20 | repository.php; api.php
SC-007 | CSRF protection | Cross-site request forgery | Inspect forms/actions | State-changing web forms verify token | Token fields and checks implemented | PASS | High | 2026-08-20 | contact.php; actions.php
SC-008 | API authentication | Unauthorized profile access | GET /me without token | 401 | Core lifecycle verified authenticated; unauthenticated retest required | NOT RUN | High
SC-009 | Website authentication gate | Unauthorized content access | Open Home/Discounts signed out | Redirect to Login | Content visible without session | FAIL | Critical | 2026-08-20 | DEF-001
SC-010 | HTTPS | Transport interception | Inspect live URL | HTTPS and valid certificate | HTTPS reachable | PASS | Critical | 2026-08-20 | live URL
SC-011 | Security headers | XSS/downgrade/MIME sniff | Inspect response headers | CSP, HSTS and nosniff | Live login returned CSP, HSTS, nosniff, DENY framing and strict referrer policy | PASS | High | 2026-08-20 | Post-deployment live headers; DEF-003 closed
SC-012 | Rate limiting | Credential/reset abuse | Inspect migration/actions; execute threshold test | 429 after configured threshold | Implementation exists; live threshold not stress-tested | NOT RUN | High |  | 005_api_rate_limits.sql
SC-013 | Secrets excluded | Credential leak | Search tracked files/history | No real keys/passwords committed | Full repository/history secret scan not recorded | NOT RUN | Critical |  | Run gitleaks
SC-014 | Authorization of admin routes | Privilege escalation | Try member and signed-out requests | 403/redirect; no CRUD | Signed-out live admin routes redirect; isolated member-role and immediate role-revocation tests passed | PASS | Critical | 2026-08-20 | admin-database-integration.sh; live route matrix
SC-015 | Account deletion | Data retention | Delete disposable account | Account deleted; sessions/attendance removed | 200 deleted=true | PASS | High | 2026-08-20 | live JSON
SC-016 | Administrator session limits | Stolen/stale privileged session | Inspect configuration and expiry logic; run isolated role-version test | 30-minute idle, eight-hour absolute and auth_version invalidation | Implemented; role change invalidated existing session in isolated MySQL | PASS | Critical | 2026-08-20 | app/auth.php; admin integration
SC-017 | Optimistic locking | Silent concurrent overwrite | Submit stale row_version after a newer update | Stale update rejected | Isolated MySQL stale event update was rejected | PASS | High | 2026-08-20 | migration 007; admin integration
SC-018 | Administrator audit trail | Unattributed privileged change | Perform protected grant/lifecycle action and inspect audit | Actor, action, entity, before/after, reason and time recorded | Production role grant audited; isolated lifecycle audit persisted | PASS | High | 2026-08-20 | admin_audit_log; admin audit
SC-019 | Production backup restoration | Unrecoverable data loss | Validate compressed backup and restore into isolated database | Backup restores schema/data and current migration | 15 tables, migration 007 and four security columns restored; temporary database removed | PASS | Critical | 2026-08-20 | Protected operational record
SC-020 | Production demo-mode protection | Known fallback administrator access | Inspect production configuration and login output | Demo mode disabled; no known credentials exposed | ALLOW_DEMO_MODE=false; live login contains no legacy demo credentials | PASS | Critical | 2026-08-20 | Production variables + live HTML

## UAT Task Sheet
User Acceptance Test — Six BKK Participants Aged 60+
This sheet is intentionally uncompleted. Names, signatures, ratings and observations must come from real external participants and cannot be manufactured.
Task ID | Must task | Success criterion | P1 | P2 | P3 | P4 | P5 | P6 | Notes/evidence
UAT-01 | Sign in using an existing account | Completes without help
UAT-02 | Return Home after opening another section | Uses navigation without prompting
UAT-03 | Find an event and explain time/location | Identifies correct details
UAT-04 | Confirm and cancel attendance | Both server-confirmed states understood
UAT-05 | Recognise demonstration event as not real | Does not attempt travel/RSVP
UAT-06 | Find a discount and explain claim process | Explains eligibility and instructions
UAT-07 | Find local service phone number | Reads correct number
UAT-08 | Contact BKK for help | Submits valid message or uses listed contact
UAT-09 | Request reset code and create password | Completes using real inbox
UAT-10 | Sign out | Returns to Login and protected content is inaccessible
Participant | Name | Age/role | Device/browser | Independent tasks /10 | Ease rating /5 | Critical defect? | Signature/date | Evidence ref | Main observation
P1
P2
P3
P4
P5
P6
Acceptance criteria
All Must tasks | Pass without a critical defect
Independent completion | >=80% across all recorded tasks
Ease rating | Average >=4/5
Accessibility | Core tasks repeated at 200% and with TalkBack/VoiceOver
Evidence | Signed sheets/photo/email permission and anonymised notes attached

## Defect Log
Defect Log
Open defects remain visible until a dated retest proves closure. A code change alone is not accepted as a passed retest.
Defect ID | Title | Area | Severity | Found date | Steps to reproduce | Expected | Actual | Root cause/status | Owner | Retest | Evidence
DEF-001 | Website bypasses required login landing page | Web/Auth | Critical | 2026-08-14 | Clear session; open / or /discounts.php | Redirect to Login | Protected member content displays with HTTP 200 | OPEN — public page routing does not enforce intended gate | Kagiso Mmatloa | FAIL 2026-08-20 | live JSON
DEF-002 | Real password-reset email not evidenced | Email/Auth | Critical | 2026-08-14 | Request code for real registered inbox | Code arrives and can reset password | Known-account request accepted and active hashed token created; mailbox receipt and successful code consumption not yet witnessed | OPEN EVIDENCE GAP — server-side request path now succeeds; end-to-end inbox/reset proof still required | Kagiso Mmatloa | PARTIAL 2026-08-20 | Live request + DB token state; redacted inbox/reset screenshot required
DEF-003 | Security response headers absent | Web/API | High | 2026-08-20 | Inspect live /health, /ready and API response headers | HSTS, CSP and nosniff present | CSP, HSTS, nosniff, DENY framing and strict referrer policy returned after deployment | CLOSED — security headers configured and live retest passed | Kagiso Mmatloa | PASS 2026-08-20 | FT-040 / SC-011 post-deployment live headers
DEF-004 | No fresh live admin CRUD evidence | Admin | High | 2026-08-20 | Log in as admin and CRUD each content type | Changes persist and display to users | Migration 007, protected admin grant, route guards and isolated lifecycle/audit tests passed; authenticated production screenshots absent | OPEN EVIDENCE GAP — implementation is deployed; only the authenticated live UI evidence set remains | Masase Mukhinindi | PARTIAL PASS 2026-08-20 | docs/ADMIN_AUDIT_2026-08-20.md; attach live before/after screenshots
DEF-005 | Real FCM delivery not tested | Android/Notifications | High | 2026-08-14 | Register physical device; publish discount/schedule reminder | One correct notification and deep link | Firebase credentials/evidence absent | BLOCKED BY EXTERNAL CREDENTIALS | Ipeleng Sithole | BLOCKED | google-services.json + device evidence
DEF-006 | Live RSVP journey lacks safe real test event | Attendance | High | 2026-08-20 | Confirm/cancel on published test event | Server-confirmed changes without false success | Only demonstration event returned and intentionally rejects attendance | BLOCKED BY TEST DATA | Blessing Rugoyi | BLOCKED | Create labelled test event with approval
DEF-007 | Manual accessibility/physical-device evidence absent | Accessibility | High | 2026-08-14 | Run 200% scale and screen-reader tasks | All core tasks independently complete | Not run | OPEN TEST GAP | Ipeleng Sithole | NOT RUN | Signed accessibility checklist
DEF-008 | Six-person elderly UAT not completed | UAT | Critical | 2026-08-14 | Facilitate ten tasks with six external users | Meets all acceptance thresholds | No participant data/sign-off | OPEN — cannot be manufactured | Blessing Rugoyi | NOT RUN | UAT Task Sheet
DEF-009 | Reported mobile slowness lacks profiler measurement | Performance | Medium | 2026-08-14 | Profile cold launch, list rendering and API calls | Within defined budgets | User perceived app as slow; cause not isolated | OPEN TEST GAP | Ipeleng Sithole | NOT RUN | Android Profiler trace
DEF-010 | iOS full login/navigation journey interrupted | iOS | High | 2026-08-14 | Clean install; sign in; navigate five tabs; sign out | Journey completes and returns to Login | Automation interrupted before assertion | OPEN RETEST | Ipeleng Sithole | NOT RUN | XCTest/manual video
DEF-011 | Resolved-contact retention job is not scheduled | Operations/Privacy | Medium | 2026-08-20 | Inspect Railway services and retention configuration | Protected scheduled job runs purge-resolved-contact-messages.php using the approved retention period | 365-day setting and purge script exist; no separate Railway scheduled service has been authorized | OPEN OPERATIONAL GAP — creating another Railway service may affect billing and requires approval | Kagiso Mmatloa | NOT RUN | ADMIN_DEPLOYMENT_CHECKLIST.md